## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Ny | Ronny | Dominic |  | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture
|  | Design architecture | Product Manager | Ronny, Ny | 4 | [7 empty] | 0
| Requirements | [11 empty] | 0
|  | Gather | Business Analyst | Domonic,Ny | 1.5 | 3 |  |  | 1 | 1 | 1 |  | 3
|  | Analyze | Business Analyst | Domonic,Ny | 1.5 | 3 |  |  | 1 | 1 | 1 |  | 3
|  | Specify | Architect | Ronny | 1.5 | 2 |  |  |  | 2 |  |  | 2
| Documentation | [11 empty] | 0
|  | Project Charter | Product Manager | Ronny | 2 | 2 |  |  | 0 | 1 | 1 |  | 2
|  | Release Plan | Product Manager | Ronny | 2 | [7 empty] | 0
|  | Requirements Document | Business Analyst, Architect | Domonic,Ny | 1 | 4 |  |  |  | 2 | 2 |  | 4
|  | Project Plan | Product Manager, Business Analyst | Ronny, Domonic, Ny | 2 | 5 |  |  | 2 | 2 | 1 |  | 5
|  | Architecture Document | Architect | Ny | 2 | 5 |  |  | 2 | 2 | 1 |  | 5
|  | User Guide & System Admin Doc | Architect | Domonic | 1.5
Coding | [12 empty] | 0
Iteration 1: | Development | [11 empty] | 0
|  | Determine technology needs | Researcher | Ronny, Domonic | 3 | 3 |  |  |  | 2 | 1
|  | Research cybersecurity requirements | Researcher | Ronny, Ny | 2 | 2 |  |  | 1 | 1
|  | Research cloud platforms | Researcher | Ny, Domonic | 2 | 3 |  |  | 1 | 1 | 1 |  | 3
|  | Analyze RAID types/combinations | Researcher | Domonic, Ny | 3 | 3 |  |  | 1 | 2 |  |  | 3
| Analysis | [11 empty] | 0
|  | Analyze / review current findings | Analyst | Ny | 2 | 3 |  |  | 3 |  |  |  | 3
|  | Evaluate needs for next iteration | Project Manager | Ronny | 4 | 2 |  |  | 2 |  |  |  | 2
Total |  |  |  |  | 35 | 40 |  | 0 | 14 | 17 | 9 | 0 | 40
Iteration 2: | Research | [6 empty] | 0 |  |  |  |  | 0
|  | Combining research for the technology | Product Manager/Research | Ronny | 2 | 3 |  |  |  | 3
|  | Designing the network | Architect | Domonic, Ny | 5 | 4 |  |  | 2 |  | 2 |  | 4
|  | Research Spambot | Product Manager | Ronny, Ny | 2 | 3 |  |  | 1 | 2
|  | Research RAID 0,1,2,3,4 | Architect | Domonic | 3 | 3 |  |  |  | 3
|  | Network Requirements | Architect | Domonic, Ny | 4 | 4 |  |  | 2 |  | 2 |  | 4
|  | Research WiFi Access Restrictions | Product Manager, Research | Ronny, Ny | 2 | 3 |  |  | 2 | 1
|  | Analyze / review current findings | Architect | Domonic | 2 | 2 |  |  |  |  | 2 |  | 2
|  | Evaluate needs for next iteration | Product Manager | Ronny | 2 | 2 |  |  |  | 2
Total |  |  |  |  | 70 | 77 |  | 0 |  |  |  | 0
Iteration 3: | Design | [6 empty] | 0 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Ronny | 3 | 2 |  |  |  | 2 |  |  | 2
|  | Risk analysis | Project Manager | Ronny, Ny | 2 | 2 |  |  |  | 2 |  |  | 2
|  | Create Network Graphics | Designer | Domonic | 5 | 3 |  |  |  |  | 3
| Development | [11 empty] | 0
|  | Review requirements | Project Manager, Designer | Ronny, Ny | 3 | 2 |  |  | 2 |  |  |  | 2
|  | Research the client's customers | Project Manager | Ronny | 8 | 5 |  |  |  | 3 | 2 |  | 5
| Analysis | [11 empty] | 0
|  | Analyze / review current findings | Project Manager | Ronny | 3 | 2 |  |  |  | 2
|  | Evaluate needs for next iteration | Tester, Developer | Domonic, Ny | 2 | 2 |  |  | 1 |  | 1
Total
Iteration 4: | Development | [6 empty] | 0 |  |  |  |  | 0
|  | Create Network Diagram | Product Manager | Ronny | 2 | 3 |  |  | 1 | 2
|  | Network Setup | Architect | Domonic | 3 | 3 |  |  |  | 3
|  | Network documentation | Architect | Domonic, Ny | 4 | 4 |  |  | 2 |  | 2 |  | 4
|  | Analyze / review current findings | Architect | Ny | 2 | 2 |  |  |  |  | 2 |  | 2
|  | Evaluate needs for next iteration | Product Manager | Ronny | 2 | 2 |  |  |  | 2
Total | [7 empty] | 0 |  |  |  | 0
Iteration 5: | Development | [11 empty] | 0
|  | User Guide | Project Manager | Ronny, Ny | 4 | 3 |  |  | 1 | 1 | 1 | 1
|  | System Documentation | Architect | Ny, Domonic | 4 | 3 |  |  | 1 | 1 | 1 | 1 | 4
|  | Test Plan | Architect | Domonic, Ny | 5 | 3 |  |  | 1 | 2 | 2 |  | 5
|  | Analyze / review current findings | Analyst | Ny | 2 | 2 |  |  | 2 |  |  |  | 2
|  | Evaluate needs for next iteration | Project Manager | Ronny | 2 | 2 |  |  |  | 2 |  |  | 2
Total | [7 empty] | 0 | 11 | 18 | 11 | 2 | 42